## Features
Sl No | MedPro Features
F1 | It gives a narration describing the health issue of concern using voice
F2 | It asks user set of questions and record their response as a narrative (story) of an anonymous user
F3 | It allows users to listen to a particular story of another person without requiring extensive navigation

## ProductBackLog
Product Backlog for MedPro
ID | User Story | Estimation(Story Points) | Priority
MP_US1 | As a user, I should be able to see all the options on the Home screen to use the application | 8 | High | ** User stories are prioritized based on the business value**
MP_US2 | As a user, I should be able to navigate from any screen to Home screen so that I would be able to see the list of Menu available. | 3 | Medium
MP_US3 | As a user, i should be able to hear a set of questions so that I can understand what is being asked. | 5 | High
MP_US4 | As a User, I should be able to record my answer to particular question so that my answers are recorded. | 5 | High
MP_US5 | As a user, I should be able to hear the options available to navigate so I can understand to perform required actions. | 3 | Low
MP_US6 | As a user, I should be able to submit my narrated stories, so my stories are saved. | 8 | High
MP_US7 | As a user, I can review my narrated story so that I can make decision to submit or not. | 3 | Low
MP_US8 | As a user, i want to see list of Stories so i can access all the recorded narrated stories by others. | 5 | High
MP_US9 | As a user, i can click on any particular story so that i can listen to them. | 2 | Medium
** Using Planning poker estimation, the user stories were estimated by team members considering MP_US4 as a average which is 5 Story points **

## Tasks
ID | User Stories | Tasks | Estimated Ideal Hours
MP_US1 | As a user, I should be able to see all the options on the Home screen to use the application | 1.1 Design of home screen User Interface with all menus | 6
|  | 1.2 Design of the Q&A User Interface | 4
|  | 1.3 Design of User Interface for List of stories | 4
|  | 1.4 Specify Acceptance Tests | 2
MP_US2 | As a user, I should be able to navigate from any screen to Home screen so that I would be able to see the list of Menu available. | 2.1 Design of Navigation Icons and Proper navigation between screens | 3
|  | 2.2 Validation of Proper Navigation between Screens | 2
|  | 2.3 Specify Acceptance Tests | 2
MP_US3 | As a user, i should be to hear a set of questions so that I can understand what is being asked. | 3.1 Formulate the Set of Questions Required | 3
|  | 3.2 Design audio and play icons for each questions | 4
|  | 3.3 Design help audio and icons | 4
|  | 3.4 Specify Acceptance Tests | 2
MP_US4 | As a User, I should be able to record my answer to particular question so that my answers are recorded. | 4.1 Design record icons and Store the recorded data | 4
|  | 4.2 Specify Acceptance Tests | 2
MP_US5 | As a user, I should be able to hear the options available to navigate so I can understand to perform required actions. | 5.1 Design of audio for navigation options available | 5
|  | 5.2 Specify Acceptance Test | 2
MP_US6 | As a user, I should be able to submit my narrated stories, so my stories are saved. | 6.1 Design of submit option and response | 3
|  | 6.2 Database Creation and schemes | 5
|  | 6.3 Database connection establish | 2
|  | 6.4 Specify Acceptance Test | 2
MP_US7 | As a user, I can review my narrated story so that I can make decision to submit or not. | 7.1 Design of User Interface for Confirmation to submit recording | 4
|  | 7.2 Design of play option to hear current narrated story | 4
|  | 7.3 Specify Acceptance test | 2
MP_US8 | As a user, i want to see list of Stories so i can access all the recorded narrated stories by others. | 8.1 Design of User Interface to list down all the recorded stories | 5
|  | 8.2 Specify Acceptance Test | 2
MP_US9 | As a user, i can click on any particular story so that i can listen to them. | 9.1 Design of User Interface to play selected story. | 3
|  | 9.2 Specify Acceptance Test | 2

## Sprint1_Tasks
Tasks | Estimated Ideal Hours
1.1 Design of home screen User Interface with all menus | 6
1.2 Design of the Q&A User Interface | 4
1.3 Design of User Interface for List of stories | 4
1.4 Specify Acceptance Tests | 2
2.1 Design of Navigation Icons and Proper navigation between screens | 3
2.2 Validation of Proper Navigation between Screens | 2
2.3 Specify Acceptance Tests | 2
3.1 Formulate the Set of Questions Required | 3
3.2 Design audio and play icons for each questions | 4
3.3 Design help audio and icons | 4
3.4 Specify Acceptance Tests | 2
4.1 Design record icons and Store the recorded data | 4
4.2 Specify Acceptance Tests | 2
5.1 Design of audio for navigation options available | 5
5.2 Specify Acceptance Test | 2
7.1 Design of User Interface for Confirmation to submit recording | 4
7.2 Design of play option to hear current narrated story | 4
7.3 Specify Acceptance test | 2
Total Hours = | 59
Miscellaneous Tasks -
1. Creation of Persona
2. Creation of narrated story board
3. Creation of product backlog and estimation of each user stories
4. Usability Testing
The Tasks for Sprint1 is considered based on the Scope assessment. where in on an average, each person in team works 10 hours per week.
Number of resources = 6
Productive Effort per week = 4-5 hrs
Each Iteration is 2 weeks, therefore available hours between 6*4*2 to 6*5*2
ie. 48 to 60 hours.
* Productive effort doesnt include time spent on meetings, discovery and others..

## Sprint2_Tasks
Tasks | Estimated Ideal Hours
6.1 Design of submit option and response | 3
6.2 Database Creation and schemes | 5
6.3 Database connection establish | 2
6.4 Specify Acceptance Test | 2
8.1 Design of User Interface to list down all the recorded stories | 5
8.2 Specify Acceptance Test | 2
9.1 Design of User Interface to play selected story. | 3
9.2 Specify Acceptance Test | 2
Total Hours = | 24

## Sprint1_Planning
Tasks | Assigned To | Planned start Date | Planned End Date | Actual Start Date | Actual End Date | Status
1.1 Design of home screen User Interface with all menus | Surya | 2019-11-07 | 2019-11-08 | 2019-11-07 | 2019-11-08 | Complete
1.2 Design of the Q&A User Interface | Shruthi | 2019-11-07 | 2019-11-07 | 2019-11-07 | 2019-11-07 | Complete
1.3 Design of User Interface for List of stories | Hina | 2019-11-08 | 2019-11-08 | 2019-11-08 | 2019-11-08 | Complete
1.4 Specify Acceptance Tests | Nivetha | 2019-11-08 | 2019-11-08 | 2019-11-08 | 2019-11-08 | Complete
2.1 Design of Navigation Icons and Proper navigation between screen | Sahana | 2019-11-07 | 2019-11-08 | 2019-11-07 | 2019-11-08 | Complete
2.2 Validation of Proper Navigation between Screens | Anusha | 2019-11-07 | 2019-11-08 | 2019-11-07 | 2019-11-08 | Complete
2.3 Specify Acceptance Tests | Hina | 2019-11-11 | 2019-11-11 | 2019-11-11 | 2019-11-11 | Complete
3.1 Formulate the Set of Questions Required | Nivetha | 2019-11-11 | 2019-11-11 | 2019-11-11 | 2019-11-11 | Complete
3.2 Design audio and play icons for each questions | Shruthi | 2019-11-08 | 2019-11-11 | 2019-11-08 | 2019-11-11 | Complete
3.3 Design help audio and icons | Anusha | 2019-11-11 | 2019-11-12 | 2019-11-11 | 2019-11-12 | Complete
3.4 Specify Acceptance Tests | Surya | 2019-11-11 | 2019-11-11 | 2019-11-11 | 2019-11-11 | Complete
4.1 Design record icons and Store the recorded data | Sahana | 2019-11-11 | 2019-11-12 | 2019-11-11 | 2019-11-12 | Complete
4.2 Specify Acceptance Tests | Anusha | 2019-11-13 | 2019-11-13 | 2019-11-13 | 2019-11-13 | Complete
5.1 Design of audio for navigation options available | Surya | 2019-11-12 | 2019-11-13 | 2019-11-12 | 2019-11-13 | Complete
5.2 Specify Acceptance Test | Sahana | 2019-11-13 | 2019-11-13 | 2019-11-13 | 2019-11-13 | Complete
7.1 Design of User Interface for Confirmation to submit recording | Nivetha | 2019-11-12 | 2019-11-13 | 2019-11-12 | 2019-11-13 | Complete
7.2 Design of play option to hear current narrated story | Hina | 2019-11-12 | 2019-11-13 | 2019-11-12 | 2019-11-13 | Complete
7.3 Specify Acceptance test | Shruthi | 2019-11-14 | 2019-11-14 | 2019-11-14 | 2019-11-14 | Complete
Team Members :
Surya
Shruthi
Hina
Nivetha
Anusha
Sahana
Status :
Backlog
To-Do
Inprogress
Review
Complete